## Slide 1
Growth FY27 Forward Look
Prioritised Roadmap & Release Breakdown
January 2026

## Slide 2
FY27 Delivery Roadmap
5 releases mapped around external constraints
Q1 (Apr-Jun)
Q2 (Jul-Sep)
Q3 (Oct-Dec)
Q4 (Jan-Mar)
FSMA: Blocks until Apr 2nd
PEGA FREEZE: Jun-Sep (No MAP changes)
Pega Go-Live: Sep 26
PHASE 2a May
JUNE Jun
SEPT Sep
NOV Nov
MAR 2027 Mar
Release timing is driven by constraints, not just priority. We're using the freeze period strategically - completing development so we're ready when slots open.

## Slide 3
Release Summary
What's in each release
PHASE 2a (2)
MGS-12826: Enhance OLBM document upload...
MGS-12838: Phase 2a - Product fee and LTV...
JUNE (5)
MGS-12833: Enhance document upload capabilities
MGS-12830: DD Bank validation ESB Service
MGS-12842: CRA enhancements - June target
MGS-13102: Prevent Special Characters entered...
MGS-13079: Remove restriction on CC seeing...
SEPT (5)
MGS-13098: Increase levels of robot validation
MGS-13105: Robot to park data entry exceptions...
MGS-13077: Remove restriction on BDM seeing...
MGS-13070: Make case status visible in Case...
MGS-12827: Remove Valuation Visibility...
NOV (2)
MGS-12832: Existing Customer Online Application
MGS-12831: Worldpay to Global Pay
MAR 2027 (19)
MGS-13067: Create new fields to identify...
MGS-13066: Create Variable Income fields and...
MGS-13062: Create new fields for Joint...
MGS-13063: Create additional fields for Self...
MGS-12823: Create Secondary Income fields and...
MGS-13096: Improve clarity of messages in...
MGS-12841: Replacement Mortgage Illustrator...
MGS-13092: Add date of valuation to MAP chaser...
MGS-13086: Improve MAP email templates
MGS-13083: Improve wording of MAP chaser emails
MGS-13073: Make offer status and timescales...
MGS-12839: Reduce AIP Queries to Underwriters
+7 more items

## Slide 4
Release: PHASE 2a
Growth Phase 2a - 2 items
Case Segmentation: 0
Communications: 1
Operational Efficiencies: 1
# | WSJF | Key | Objective | Summary
3 | 9.4 | MGS-12826 | Communications | Enhance OLBM document upload messaging for case types
13 | 6.0 | MGS-12838 | Operational Efficiencies | Phase 2a - Product fee and LTV Enhancements

## Slide 5
Release: JUNE
Growth June Release - 5 items
Case Segmentation: 0
Communications: 1
Operational Efficiencies: 4
# | WSJF | Key | Objective | Summary
7 | 8.0 | MGS-12833 | Operational Efficiencies | Enhance document upload capabilities
16 | 5.0 | MGS-12830 | Operational Efficiencies | DD Bank validation ESB Service
24 | 2.8 | MGS-12842 | Operational Efficiencies | CRA enhancements - June target
33 | 1.6 | MGS-13102 | Operational Efficiencies | Prevent Special Characters entered in OLBM causing robots to...
34 | 1.6 | MGS-13079 | Communications | Remove restriction on CC seeing property valuation details

## Slide 6
Release: SEPT
Growth September Release - 5 items
Case Segmentation: 0
Communications: 3
Operational Efficiencies: 2
# | WSJF | Key | Objective | Summary
15 | 5.2 | MGS-13098 | Operational Efficiencies | Increase levels of robot validation
32 | 1.9 | MGS-13105 | Operational Efficiencies | Robot to park data entry exceptions until all acceptable dat...
35 | 1.6 | MGS-13077 | Communications | Remove restriction on BDM seeing property valuation details
39 | 0.8 | MGS-13070 | Communications | Make case status visible in Case Tracker
40 | 0.8 | MGS-12827 | Communications | Remove Valuation Visibility Restrictions

## Slide 7
Release: NOV
Growth November Release - 2 items
Case Segmentation: 0
Communications: 0
Operational Efficiencies: 2
# | WSJF | Key | Objective | Summary
28 | 2.4 | MGS-12832 | Operational Efficiencies | Existing Customer Online Application
31 | 2.0 | MGS-12831 | Operational Efficiencies | Worldpay to Global Pay

## Slide 8
Release: MAR 2027
Growth 2027 Release - 19 items
Case Segmentation: 6
Communications: 7
Operational Efficiencies: 6
# | WSJF | Key | Objective | Summary
4 | 8.0 | MGS-13067 | Case Segmentation | Create new fields to identify Second/Holiday Home's and pass...
5 | 8.0 | MGS-13066 | Case Segmentation | Create Variable Income fields and pass data to PCO
6 | 8.0 | MGS-13062 | Case Segmentation | Create new fields for Joint Borrower Sole Owner cases and pa...
8 | 7.4 | MGS-13063 | Case Segmentation | Create additional fields for Self Employed (Main Income)
9 | 7.4 | MGS-12823 | Case Segmentation | Create Secondary Income fields and pass to PCO
18 | 3.8 | MGS-13096 | Communications | Improve clarity of messages in post-document review emails
19 | 3.4 | MGS-12841 | Operational Efficiencies | Replacement Mortgage Illustrator tool
20 | 3.2 | MGS-13092 | Communications | Add date of valuation to MAP chaser letter
21 | 3.2 | MGS-13086 | Communications | Improve MAP email templates
22 | 3.2 | MGS-13083 | Communications | Improve wording of MAP chaser emails
23 | 3.2 | MGS-13073 | Communications | Make offer status and timescales visible in OLBM and MAP
25 | 2.8 | MGS-12839 | Operational Efficiencies | Reduce AIP Queries to Underwriters
+ 7 more items - see Jira for full list