## Slide 1
Growth FY27 Forward Look
Prioritised Roadmap & Release Breakdown
January 2026

## Slide 2
FY27 Delivery Roadmap
5 releases mapped around external constraints
Q1 (Apr-Jun)
Q2 (Jul-Sep)
Q3 (Oct-Dec)
Q4 (Jan-Mar)
FSMA: Blocks until Apr 2nd
PEGA FREEZE: Jun-Sep (No MAP changes)
Pega Go-Live: Sep 26
PHASE 2a May
JUNE Jun
SEPT Sep
NOV Nov
MAR 2027 Mar
Release timing is driven by constraints, not just priority. We're using the freeze period strategically - completing development so we're ready when slots open.

## Slide 3
Release Summary
What's in each release
PHASE 2a 2 items
#3 MGS-12826
Enhance OLBM document upload messaging f...
#13 MGS-12838
Phase 2a - Product fee and LTV Enhanceme...
JUNE 5 items
#7 MGS-12833
Enhance document upload capabilities
#16 MGS-12830
DD Bank validation ESB Service
#24 MGS-12842
CRA enhancements - June target
#33 MGS-13102
Prevent Special Characters entered in OL...
#34 MGS-13079
Remove restriction on CC seeing property...
SEPT 5 items
#15 MGS-13098
Increase levels of robot validation
#32 MGS-13105
Robot to park data entry exceptions unti...
#35 MGS-13077
Remove restriction on BDM seeing propert...
#39 MGS-13070
Make case status visible in Case Tracker
#40 MGS-12827
Remove Valuation Visibility Restrictions
NOV 2 items
#28 MGS-12832
Existing Customer Online Application
#31 MGS-12831
Worldpay to Global Pay
MAR 2027 19 items
#4 MGS-13067
Create new fields to identify Second/Hol...
#5 MGS-13066
Create Variable Income fields and pass d...
#6 MGS-13062
Create new fields for Joint Borrower Sol...
#8 MGS-13063
Create additional fields for Self Employ...
#9 MGS-12823
Create Secondary Income fields and pass ...
#18 MGS-13096
Improve clarity of messages in post-docu...
#19 MGS-12841
Replacement Mortgage Illustrator tool
#20 MGS-13092
Add date of valuation to MAP chaser lett...
#21 MGS-13086
Improve MAP email templates
#22 MGS-13083
Improve wording of MAP chaser emails
+9 more

## Slide 4
Release: PHASE 2a
Growth Phase 2a - 2 items
Case Segmentation: 0
Communications: 1
Operational Efficiencies: 1
# | WSJF | Key | Objective | Summary
3 | 9.4 | MGS-12826 | Communications | Enhance OLBM document upload messaging for case types
13 | 6.0 | MGS-12838 | Operational Efficiencies | Phase 2a - Product fee and LTV Enhancements

## Slide 5
Release: JUNE
Growth June Release - 5 items
Case Segmentation: 0
Communications: 1
Operational Efficiencies: 4
# | WSJF | Key | Objective | Summary
7 | 8.0 | MGS-12833 | Operational Efficiencies | Enhance document upload capabilities
16 | 5.0 | MGS-12830 | Operational Efficiencies | DD Bank validation ESB Service
24 | 2.8 | MGS-12842 | Operational Efficiencies | CRA enhancements - June target
33 | 1.6 | MGS-13102 | Operational Efficiencies | Prevent Special Characters entered in OLBM causing robots to...
34 | 1.6 | MGS-13079 | Communications | Remove restriction on CC seeing property valuation details

## Slide 6
Release: SEPT
Growth September Release - 5 items
Case Segmentation: 0
Communications: 3
Operational Efficiencies: 2
# | WSJF | Key | Objective | Summary
15 | 5.2 | MGS-13098 | Operational Efficiencies | Increase levels of robot validation
32 | 1.9 | MGS-13105 | Operational Efficiencies | Robot to park data entry exceptions until all acceptable dat...
35 | 1.6 | MGS-13077 | Communications | Remove restriction on BDM seeing property valuation details
39 | 0.8 | MGS-13070 | Communications | Make case status visible in Case Tracker
40 | 0.8 | MGS-12827 | Communications | Remove Valuation Visibility Restrictions

## Slide 7
Release: NOV
Growth November Release - 2 items
Case Segmentation: 0
Communications: 0
Operational Efficiencies: 2
# | WSJF | Key | Objective | Summary
28 | 2.4 | MGS-12832 | Operational Efficiencies | Existing Customer Online Application
31 | 2.0 | MGS-12831 | Operational Efficiencies | Worldpay to Global Pay

## Slide 8
Release: MAR 2027
Growth 2027 Release - 19 items
Case Segmentation: 6
Communications: 7
Operational Efficiencies: 6
# | WSJF | Key | Objective | Summary
4 | 8.0 | MGS-13067 | Case Segmentation | Create new fields to identify Second/Holiday Home's and pass...
5 | 8.0 | MGS-13066 | Case Segmentation | Create Variable Income fields and pass data to PCO
6 | 8.0 | MGS-13062 | Case Segmentation | Create new fields for Joint Borrower Sole Owner cases and pa...
8 | 7.4 | MGS-13063 | Case Segmentation | Create additional fields for Self Employed (Main Income)
9 | 7.4 | MGS-12823 | Case Segmentation | Create Secondary Income fields and pass to PCO
18 | 3.8 | MGS-13096 | Communications | Improve clarity of messages in post-document review emails
19 | 3.4 | MGS-12841 | Operational Efficiencies | Replacement Mortgage Illustrator tool
20 | 3.2 | MGS-13092 | Communications | Add date of valuation to MAP chaser letter
21 | 3.2 | MGS-13086 | Communications | Improve MAP email templates
22 | 3.2 | MGS-13083 | Communications | Improve wording of MAP chaser emails
23 | 3.2 | MGS-13073 | Communications | Make offer status and timescales visible in OLBM and MAP
25 | 2.8 | MGS-12839 | Operational Efficiencies | Reduce AIP Queries to Underwriters
+ 7 more items - see Jira for full list