## Slide 1
Mortgage Systems Value Stream Delivery
1
NBS Confidential
Michael James
Delivery Lead
Value Stream
Growth
Origination
Waracle, 10to8, Case Seg*
*re-prioritised
Brochureware
BAU & Direct Website
Re-platform, CBIS Rebrand
SAM Replacement
Graeme Cumming
Collate Migration
Growth
1x BA 2x Delivery 2x QE
Brochureware
1x BA 2x .NET Dev 2x QE
SAM Replacement
3x BA 2x Delivery 1x Design 3x Java Dev 7x QE
FY27: 26 FTE
Growth: 5
Brochureware: 5
SAM: 16

## Slide 2
Value Stream Roadmap
2
NBS Confidential
Q4 2025
Q1 2026
Q2 2026
Q3 2026
Q4 2026
2027
Waracle Calculator
Go Live
Direct Website
CBIS Rebrand
Re-platform
FSMA Cutover
Growth Ops
10to8 & Live Chat
Growth Comms
Broker Comms Strategy
SAM Replacement
Discovery
Decision
Implementation
Go Live
Today
◆ Confirmed milestone ◆ TBC/In planning

## Slide 3
L0 & L1 Milestones
3
NBS Confidential
L0 Objectives
Objective
L0 Target
RAG
Owner
Waracle Calculator
11 Feb 2026
Green
Michael James
Direct Website Re-platform
02 Apr 2026
Green
Michael James
Growth - Operational Efficiencies
31 Mar 2027
Green
Michael James
Growth - Communications
31 Mar 2027
Green
Michael James
Growth - Case Segmentation
31 Mar 2027
Green
Michael James
SAM Replacement
31 Dec 2026
Green
Graeme Cumming
Key L1 Milestones (Next 90 Days)
Milestone
Parent L0
Due
RAG
CB AFCALC Governance
Waracle
10 Feb
Green
CBIS Rebranding
Direct Website
10 Feb
Green
10to8 Appointment Booking
Growth Ops
18 Feb
Green
Re-platform Clydesdale Direct
Direct Website
20 Feb
Green
CB AFCALC Review & Rebuild
Waracle
27 Feb
Green
SAM Discovery Complete
SAM
27 Feb
Green
FSMA Part VII Cutover
Direct Website
02 Apr
Green
SAM Decision
SAM
03 Apr
Green

## Slide 4
Risks & Key Challenges
4
NBS Confidential
Open Risks
Risk
Workstream
RAG
Target
Owner
Waracle 3rd party dependency
Waracle
Green
28 Feb
Michael James
SAM Collate Capabilities
SAM
Amber
27 Mar
Graeme Cumming
SAM not replaced in time
SAM
Amber
27 Feb
Graeme Cumming
Key Challenges
• Waracle delivery tight (11 Feb) - governance sign-off in progress
• SAM vendor decision pending (Q2) - Collate capability validation ongoing
• Growth Case Segmentation re-prioritised to focus on 10to8 & Live Chat
• Direct Website FSMA cutover dependent on Part VII programme